## Sheet1
|  |  | but 2x6's cut for 4 more, osb for 2 more, 5.8" copper for 2 or 3, and 2x4 for 2 more |  |  |  | Completed Pannels | 6
[7 empty] | Total Time | 1900-01-01 04:51
Date | time start | time finish | lunch / distractions | Did what |  | elapsed time | Time / pannel | 0.36701
1
[9 empty] | quantity | 6
[6 empty] | 0 |  | Gary's estimation
2008-12-26 | 13:00 | 17:30 |  | cut wood ( 2x4,2x6) |  | 0.1875 |  | cut / clean manifold | 2 | 12
2008-12-27 | 9:00 | 17:00 | 0:30 | cut wood, cut copper and assembled 1 copper loop |  | 0.3125 |  | mold aluminum | 0.25 | 1.5
2008-12-28 | 16:00 | 17:45 |  | cut / painted OSB, 8 sheets |  | 0.072917 |  | fins to absorber | 1.75 | 10.5
2008-12-29 | 19:00 | 20:30 |  | cut copper for 6 loops except for 40 5.8" pcs. Internally deburred all and externally deburred 5.8" sections |  | 0.0625 |  | paint | 0.5 | 3
2008-12-30 | 19:45 | 21:00 |  | deburred 8' copper externally, made 2 copper assemblies |  | 0.052083 |  | frame | 0.5 | 3
2009-01-01 | 11:30 | 12:55 |  | cut 1.75: sections for inlet / outlet of copper, assembled test ports, soldered ends on 3 arrays, pressure tested 3 arrays |  | 0.059028 |  | insulation | 0.25 | 1.5
| 12:55 | 13:45 |  | assembled copper assy, soldered 1/2 |  | 0.034722 |  | glazing | 0.75 | 4.5
| 14:30 | 14:40 |  | soldered other half ( used 2 torches) |  | 0.0069444 |  | thinking | 1 | 6
| 14:50 | 16:00 |  | cut 42 5.8" copper lengths and fully deburred / deoxidixed. Built, soldered, and pressure tested 1 array |  | 0.048611
| 16:00 | 16:30 |  | assemled / soldered one assembly |  | 0.020833 |  | total | 7 | 42
| 16:30 | 17:45 |  | finished 2 big cuts on all 2/6's |  | 0.052083
2009-01-02 | 10:30 | 11:35 |  | retested copper, setup for making absorbers |  | 0.045139
| 12:15 | 13:35 |  | pannel 1 made |  | 0.055556
| 12:15 | 13:35 | 1:00 | aluminum stamped | reduced due to learning | 0.013889
| 14:35 | 15:30 |  | pannel screwed and framed |  | 0.038194
| 15:40 | 16:45 |  | person 2 left. Absorber 3/4 done |  | 0.045139
| 15:40 | 16:45 | 0.045139 | person 2 left. Absorber 3/4 done | reduced due to learning | 0
| 16:45 | 17:40 |  | second absorber framed and done |  | 0.038194
2008-01-03 | 11:30 | 13:55 |  | 1 abosrber assembled and framed, and mounted. aluminum stamped for it, and 2x4 end + 3 more cut |  | 0.10069
| 14:25 | 14:45 |  | started next panel |  | 0.013889
| 14:45 | 14:55 |  | stamped aluminum except cut ends |  | 0.0069444
| 14:55 | 15:30 |  | absorber assembled |  | 0.024306
| 15:37 | 15:40 |  | flipped absorber |  | 0.0020833
| 15:40 | 16:20 |  | cut 10 2/4 side pieces |  | 0.027778
| 16:20 | 16:44 |  | cut 10' 2x6 into pieces, finished end cuts. 8 secions made |  | 0.016667
| 16:44 | 17:05 |  | absorber framed |  | 0.014583
2009-01-04 | 13:50 | 14:15 |  | started absorber |  | 0.017361
| 14:15 | 14:25 |  | trimmed notch in 28 pannels for end copper T's |  | 0.0069444
| 14:25 | 14:35 |  | all pieces formed except one end side |  | 0.0069444
| 14:35 | 15:15 |  | end pieces trimmed / formed. absorber assembled. Not framed |  | 0.027778
2009-01-05 | 18:54 | 19:25 |  | framed unit |  | 0.021528
| 19:25 | 20:05 |  | absorber started |  | 0.027778
| 19:25 | 20:05 |  | absorber done |  | 0.027778
| 20:05 | 20:20 |  | frame done |  | 0.010417
| 20:05 | 20:20 |  | frame done 2 people |  | 0.010417
2009-01-11 | 12:00 | 12:35 |  | painted a few assemblies black |  | 0.024306
| 13:45 | 14:20 |  | finished painting |  | 0.024306
| 14:20 | 15:05 |  | cleaned absorbers / tested HVLP gun |  | 0.03125
| 15:05 | 15:30 |  | made paint stir stick for solar paint. |  | 0.017361
| 15:30 | 16:20 |  | paint done |  | 0.034722
| 16:20 | 16:50 |  | paint accessories cleaned up |  | 0.020833
2009-01-15 | 19:30 | 20:30 |  | drilled holes for conduit, cut some conduit |  | 0.041667
2009-01-17 | 11:00 | 11:30 |  | conduit cut / pained |  | 0.020833
| 12:00 | 12:30 |  | cut top / bottom 3/4 x 3/4's. Need to cut to length yet |  | 0.020833
| 12:30 | 12:47 |  | glued 2 pannel assy's ( single thickness) |  | 0.011806
| 13:35 | 15:20 |  | painted all trim pieces, cut rest of trim. Put in 1 insulation block |  | 0.072917
| 15:20 | 16:30 |  | pannel glazed |  | 0.048611
2009-01-18 | 14:00 | 14:05 |  | cut screws for glazing attachment |  | 0.0034722
| 14:05 | 15:00 |  | first pannel done and put away. Second pannel has insulation installed |  | 0.038194
| 15:00 | 16:00 |  | pannel finished |  | 0.041667
| 16:00 | 17:20 |  | pannel finished |  | 0.055556
2008-01-24 | 11:00 | 12:05 |  | 4th insulated, poly in place. Need to screw down |  | 0.045139
| 12:43 | 12:50 |  | screwed down top |  | 0.0048611
| 12:50 | 13:07 |  | cut / painted conduit x 3 |  | 0.011806
| 13:30 | 13:50 |  | pannel complete |  | 0.013889
| 14:00 | 14:15 |  | sealed 1\2 of 8" strips on 3, all on new pannel |  | 0.010417
| 14:15 | 14:25 |  | installed conduit on last 2 pannels |  | 0.0069444
| 14:30 | 15:41 |  | pannel finished |  | 0.049306
| 15:50 | 16:30 |  | pannel started |  | 0.027778
| 16:55 | 17:45 | 0:30 | pannel finished |  | 0.013889
0
0
0
0